## Sheet1
FORMAT FOR THE MONTHLY PROGRESS REPORT (MPR) UNDER ATMA PROGRAMME
Progress for the Month of May 2013-14 for the financial Year 2013-14 of Aurangabad District
Sl.No. | Component | Target (2012-13) |  | Achievement for the reporting month |  | Cumulative Achievement till the Reporting Month
|  | Physical | Financial | Physical | Financial | Physical | Financial
I | Farm Oriented Activities
B.1 | Developing SREPs (Numbers)
B.2 | a) Inter State | 418 | 4.18 | - | 0.96 | 225 | 2.96
| No. of Trainings |  |  |  |  | 1
| No. of Participants |  |  |  |  | 75
| Male |  |  |  |  | 75
| Female |  |  |  |  | -
| No. of Man days |  |  |  |  | 225
| b) Within State | 803 | 6.023 | - | - | 56 | 0.42
| No. of Trainings |  |  |  |  | 1
| No. of Participants |  |  |  |  | 28
| Male |  |  |  |  | 28
| Female |  |  |  |  | -
| No. of Man days |  |  |  |  | 56
| c) Within District | 2750 | 11 | 500 | 6.8865 | 800 | 7.8465
| No. of Trainings |  |  | 1 |  | 2
| No. of Participants |  |  | 500 |  | 800
| Male |  |  | 490 |  | 784
| Female |  |  | 10 |  | 16
| No. of Man days |  |  | 500 |  | 800
B.3 | Demonstration |  |  |  |  | -
| Agriculture (Nos.) | 231 | 9.24 | - | - | - | -
| Allied Sectors (Nos.) | 514 | 20.552 | - |  | - | -
| Total No. of Participants |  |  |  |  | - | -
| No. of CIG |  |  |  |  | - | -
| No. of Individual Farmers |  |  |  |  | - | -
| No. of Male Farmers |  |  |  |  | - | -
| No. of Female Farmers |  |  |  |  | - | -
B.4 | Exposure Visit |  |  |  |  | - | -
| a) Inter State | 550 | 3.3 | - | - | - | -
| No. of EV |  |  |  |  | - | -
| No. of Participants |  |  |  |  | - | -
| Male |  |  |  |  | - | -
| Female |  |  |  |  | - | -
| No. of Man days |  |  |  |  | - | -
| b) Within State | 792 | 2.376 | - |  | - | -
| No. of EV |  |  |  |  | - | -
| No. of Participants |  |  |  |  | - | -
| Male |  |  |  |  | - | -
| Female |  |  |  |  | - | -
| No. of Man days |  |  |  |  | - | -
| c) Within District | 825 | 2.063 | - | - | - | -
| No. of EV |  |  |  |  | - | -
| No. of Participants |  |  |  |  | - | -
| Male |  |  |  |  | - | -
| Female |  |  |  |  | - | -
| No. of Man days |  |  |  |  | - | -
B.5 | Mobilization of Farmers Group |  |  |  |  | - | -
| a) Capacity Building, skill develoment and support services | 176 | 8.8 | - |  | - | -
| No. of Groups formed |  |  |  |  | - | -
| b) Seed Money/Revolving fund | 30 | 3 | - | - | - | -
B.6 | Rewards & Incentives - Best organized group representing different enterprises (5 groups) | 5 | 1 | - | - | - | -
B.7 | Farmer Awards at block level | 0 | 0 | - | - | - | -
B.8 | District level exhibitions, Kisan Melas, fruits/Vegetable shows No. of events | - | 4 | - | - | - | -
| Total no. of visitors |  |  |  |  | - | -
| Male |  |  |  |  | - | -
| Female |  |  |  |  | - | -
B.9 | Number of leaflet made and distributed Number of advertisements made | - | 4 | - | - | - | -
B.10 | Number of technology packages developed (CD) | 10 | 2 | - | - | - | -
III. | Agricultural Technology Refinement, Validation and Adoption | - | - | - | - | - | -
B.11 | Farmers Scientist Interactions at district level | 2 | 0.4 | - | - | - | -
| Designate suppt. from KVK at dist. level | 1 | 0.24 |  |  | - | -
| No. of farmers participated |  |  |  |  | - | -
| Male |  |  |  |  | - | -
| Female |  |  |  |  | - | -
B.12 | Organization of Field Days and Kisan Gosthies | 22 | 3.3 | - | - | - | -
| No. of FD/KG |  |  |  |  | - | -
| No. of farmers participated |  |  |  |  | - | -
| Male |  |  |  |  | - | -
| Female |  |  |  |  | - | -
B.13 | Assessment, refinement, validation and adoption of frontline technologies and other researchable issues through KVKs and other local research centres. | 1 | 2 | - | - | - | -
| Whether KVK involved ? |  |  |  |  | - | -
B.14 | Establishment of ATMA like institutions Recurring |  |  |  |  | - | -
| TA/DA & other Operational expenses at district level | - | 6.5 | - | 0.11 | - | 0.11
| Operational expenses at block level | 11 | 3.3 | - | - | - | -
| Hiring of vehicles | - | 1.5 | - | 0.15 | - | 0.15
| Non-Recurring |  |  |  |  | - | -
| equipment | - | - | - | - | - | -
| Civil works and Re-furbishing of ATMA office | - | - | - | - | - | -
| Support Block level-BTM | 11 | 19.8 | - |  | - | -
| Operational expenses for BTM | - | 6.6 | - | - | - | -
| Recru. Specialist & Func. Support (Establishment) | 4 | 23.04 | - | 1.3474 | - | 1.9745
| Specialist Support SMS & Operational expense-SMS | 22 | 22.44 | - | - | - | -
B.15 | Establishment of block level FIACS (Numbers) | 0 | 0 | - | - | - | -
B.16 | Farm School | 110 | 32.34 | - | - | - | -
D. | INNOVATIVE ACTIVITIES-DISTRICT LEVEL |  |  |  | - | - | -
D.1 | Support for district level Training Institutions | 1 | 5 | - | - | - | -
D.2 | Setting up CRS | 0 | 0 | - | - | - | -
| No. of applications received |  |  |  |  | - | -
| Current Status |  |  |  |  | - | -
D.3 | Farmers Friend | 0 | 0 | - | - | - | -
E. | OTHER INNOVATIVE ACTIVITIES |  |  |  |  | - | -
E.2 | Innovative activities-District component | 11 | 5.5 | - | 5.28 | - | 5.28
| Krishi Vaigyanik Gaon ki Ore |  |  |  |  | - | -
| Chief Minister Rapid Seed Exchange Programme |  |  |  |  | - | -
| Seed Village |  |  |  |  | -
| TOTAL(B.1 to E.2) | - | 213.494 | - | 14.7339 | - | 18.741
| Accountant |  | Project Director ATMA, Aurangabad
ATMA, Aurangabad

## Sheet2
Financial Summary as on 31-05-2013
ATMA, Aurangabad
1 | Opening Balance as on 01.04.2013 Central Share (1) | (-)2726095.00
2 | Opening Balance as on 01.04.2013 State Share (2) | 812809
3 | Total Opening Balance as on 01.04.2013 (3) = (1) + (2) | -
4 | Funds Received from BAMETI under Central Share up to the month in the current financial year (4) | -
5 | Funds Received from BAMETI under State Share up to the month in the current financial year (5) | -
6 | Total funds Received from BAMETI up to the month in the current financial year (6) = (4) + (5) | -
7 | Funds available up to the month under report under Central Share (7) = (1) + (4) | (-)2726095.00
8 | Funds available up to the month under report under State Share (8) = (2) + (5) | 812809
9 | Total Funds available up to the month under report (9) = (7) + (8) | 812809
10 | Unspent balance of Central Share on the last day of the month under report (upto 31.05.2013) (10) | (-)4600197.00
11 | Unspent balance of State Share on the Iast day of the month under report (upto 31.05.2013) (11) | 812809
12 | Cumulative Unspent balance on the Iast day of the month (upto 31.05.2013) under report (12)=(10)+(11) | -
Accountant Project Director
ATMA, Aurangabad ATMA, Aurangabad